## TEST CASE REPORT
KERALA WEDDING PLANNER
VERSION NO: BROWSER:Chrome OS:WINDOWS | [5 empty] | DATE:25-4-2025
VERIFIED BY: | [5 empty] | TESTED BY:ALEENA MARIA JOY
Test Case ID | Test Scenario | Test Steps | Expected Result | Actual Result | Status
TC011 | Verify About Us page loads | 1.Open the website www.weddingplannerskerala.com 2.Click on the "About Us" link | About Us page should open | Page loaded successfully | ✅ Passed
TC012 | Verify blog section access | 1.Open the URL 2.Click each item in the navigation bar 3.Verify navigation to correct pages | Blog page should open | Blog section not responding | ❌ Failed
TC013 | Check navigation consistency | 1.Open the URL 2.Click each item in the navigation bar 3.Verify each page opens as expected | Each should open its respective page | Some links don’t work | ❌ Failed
TC014 | Verify scrolling functionality | 1. Open the URL 2. Scroll down through the homepage 3. Verify all sections are displayed correctly | Page should scroll smoothly | Scrolling works well | ✅ Passed
TC015 | Check image slider functionality | 1. Open the URL 2. Locate the image slider on the homepage 3. Observe automatic and manual slide transitions | Images should transition properly | Transitions smooth | ✅ Passed
TC016 | Check FAQ section | 1. Open the URL 2. Click on the "FAQ" link in the navigation or footer 3. Verify the FAQ page loads with relevant questions | FAQs should be expandable | Section missing | ❌ Failed
TC017 | Verify testimonials section | 1. Open the URL 2. Scroll down to the testimonials section 3. Verify testimonial content is visible | Testimonials should be visible | Displayed as expected | ✅ Passed
TC018 | Verify page speed | 1.Open the website 2. Analyze the results for performance and improvements | Load time should be optimal | Slow loading | ❌ Failed
TC019 | Check spelling and grammar on homepage | 1. Open the URL 2. Read through the homepage content 3. Verify that the text is clear, accurate, and error-free | No typos or grammar errors | Some typos found | ❌ Failed
TC020 | Test search bar functionality | 1. Open the URL 2. Enter a keyword into the search bar 3. Click the search icon or press Enter 4. Verify search results appear correctly | Should display relevant results | No search bar present | ❌ Failed
TC021 | Check contact number is clickable | 1. Open the URL on a mobile device 2. Click on the phone number 3. Verify the dialer opens with the correct number | Should open dialer | Clickable and working | ✅ Passed
TC022 | Check email link | 1. Open the URL 2. Click on the email address 3. Verify the default email client opens with the address filled in | Should open email client | No response | ❌ Failed
TC023 | Verify image alt text | 1. Open the URL 2. Inspect images using browser developer tools 3. Verify each image has meaningful alt text | All images should have alt text | Alt text missing on some images | ❌ Failed
TC024 | Test website on Safari browser | 1. Open the URL in Safari browser 2. Check layout and functionality 3. Verify that the site behaves as expected | Should display properly | Looks fine | ✅ Passed
TC025 | Check 404 error page | 1. Open the base URL 2. Append a random or invalid path (e.g., /fake-page) 3. Verify that a 404 or custom error page appears | Should show custom 404 page | Generic browser error | ❌ Failed
TC026 | Verify contact form validations | 1. Open the URL 2. Locate a form on the page 3. Click submit without filling any fields 4. Verify error messages are shown | Should show validation errors | Validation working fine | ✅ Passed
TC027 | Test dropdown menu | 1. Open the URL 2. Hover over a menu item with a dropdown 3. Verify that the dropdown appears | Dropdown should appear | Dropdown visible | ✅ Passed
TC028 | Check testimonials carousel | 1. Open the URL 2. Scroll to the testimonials section 3. Click the next and previous buttons 4. Verify the testimonial content updates | Should scroll through testimonials | Does not respond | ❌ Failed
TC029 | Verify portfolio/gallery filter | 1. Open the gallery page 2. Click on various category filter buttons 3. Verify that items are filtered accordingly | Images should be filtered | Filter not working | ❌ Failed
TC030 | Test video playback | 1. Open the URL 2. Locate the embedded video 3. Click play and verify playback starts | Video should play | Video plays properly | ✅ Passed
TC031 | Verify language selector | 1. Open the URL 2. Click on the language selector 3. Select a different language and verify content changes | Should switch language | No language option present | ❌ Failed
TC032 | Verify WhatsApp chat icon | 1. Open the URL 2. Click on the WhatsApp chat icon 3. Verify it opens WhatsApp Web or the app with correct number | Should open WhatsApp chat | No response on click | ❌ Failed
TC033 | Check anchor links | 1. Open the URL 2. Click on internal links like “#about” or “#services” 3. Verify the page scrolls to the correct section | Should scroll to section | Working fine | ✅ Passed
TC034 | Verify loading spinner | 1. Open the URL 2. Press the reload/refresh button 3. Verify the page reloads without error | Loading spinner should appear | No spinner shown | ❌ Failed
TC035 | Check booking form validations | 1. Open a form on the URL 2. Leave required fields empty 3. Click submit and check for validation messages | Should show errors | Errors displayed | ✅ Passed
TC036 | Verify font consistency | 1. Open all major pages of the website 2. Observe the fonts used 3. Verify consistency and readability | Fonts should be uniform | Some pages have inconsistent fonts | ❌ Failed
TC037 | Check SSL certificate | 1. Open the URL in any web browser 2. Verify the website loads and functions properly | Should show secure padlock | SSL is active | ✅ Passed
TC038 | Check terms & conditions link | 1. Open the URL 2. Scroll to the footer 3. Click any footer link and verify the navigation | Should open Terms page | Page opens correctly | ✅ Passed
TC039 | Test blog post share buttons | 1. Open a blog post 2. Click the share icon or button 3. Verify that sharing options appear | Should trigger share options | No response | ❌ Failed
TC040 | Verify hover effects on buttons | 1. Open the URL 2. Hover over different buttons 3. Verify hover styles and interactions appear | Effect should appear | Effects working | ✅ Passed
TC041 | Check newsletter subscription | 1. Open the URL 2. Enter a valid email in the newsletter or contact form 3. Click submit and verify a confirmation message appears | Should show confirmation | Working properly | ✅ Passed
TC042 | Verify no horizontal scroll | 1. Open the URL 2. Locate any horizontal scroll sections (e.g., carousels) 3. Scroll sideways and verify smooth scrolling | No scroll bar should appear | Horizontal scroll appears | ❌ Failed
TC043 | Check privacy policy link | 1. Open the URL 2. Scroll to the footer 3. Click another link and verify redirection | Privacy policy should open | Page opens successfully | ✅ Passed
TC044 | Test contact location map | 1. Open the URL 2. Scroll to the Contact section 3. Verify the map is displayed and interactive | Map should load and be interactive | Map fails to load | ❌ Failed
TC045 | Verify redirection of social media icons | 1. Open the URL 2. Scroll to the Home Page 3.Click on Facebook, Twitter, LinkedIn, and Instagram icons | User should be redirected to the correct respective social media pages | User is redirected correctly to Facebook, Twitter, LinkedIn, and Instagram pages | ✅ Passed
TC046 | Verify Navigation Menu functionality | 1. Open the URL 2. Click on different menu items (Home, Services, Contact, etc.) | User should be navigated to the respective section | Navigation works correctly | ✅ Passed
TC047 | Verify Phone Number / Email link functionality | 1. Open the URL 2.Click on the phone number or email link | It should open the default call or email application | Phone dialer/email client opened | ✅ Passed
TC048 | Verify Mobile Responsiveness | 1. Open the URL 2.Open the site on mobile screen or inspect with mobile view | Website layout should adjust and remain functional | Mobile view working properl | ✅ Passed
TC049 | Verify Scroll Behavior | 1. Open the URL 2.Scroll up and down the homepage | Smooth scrolling without lagging | Successfully Scrolling smooth | ✅ Passed
TC050 | Verify Details of Previous Work | 1. Open the URL 2.Navigate to the section showcasing previous works | Previous event photos/details should be properly displayed | Previous works displayed correctly | ✅ Passed

## BUG REPORT
KERALA WEDDING PLANNER
BROWSER:Chrome OS:WINDOWS |  |  |  | DATE:23-4-2025
VERIFIED BY: |  |  |  | TESTED BY:ALEENA MARIA JOY
HOME
Bug_id | Bug Description | Steps to reproduce | Screenshot | Severity | Priority | Status
BUG001 | "No content found" message displayed unexpectedly | 1. Open the website www.weddingplannerskerala.com 2. Check below the navigation bar |  | Medium | High | Open
BUG002 | Navigation dropdown arrows are too small/misaligned | 1. Hover over menu items like HOME, DECOR, etc. 2. Observe dropdown arrow size |  | Low | Medium | Open
BUG003 | Low contrast on navigation bar with gradient background | 1. View the website header 2. Observe text/icons against the purple gradient |  | Medium | High | Open
BUG004 | URL not clickable despite prominent display | 1. Scroll to main banner 2. Try to click "www.weddingplannerskerala.com" text |  | Low | Medium | Open
BUG005 | Poor alignment and spacing in the banner text | 1. View the “ONE WEDDING! MEMORIES FOR LIFETIME” section 2. Notice tight spacing |  | Low | Low | Open
BUG006 | Grammatical error in tagline | 1. Read the banner tagline "ONE WEDDING! MEMORIES FOR LIFETIME" |  | Low | Medium | Open
BUG007 | Footer "Privacy Policy" link redirects to the top of the page instead of opening the policy | 1. Scroll to the footer of the page 2. Click on the "Privacy Policy" link 3. Notice it redirects to the top or nowhere instead of a separate page or modal |  | Medium | High | Open
BUG008 | Inconsistent text color styling across list items | 1. Scroll to the "Important Service Links" and "Major Locations we service" sections 2. Observe red vs. black text |  | Low | Medium | Open
BUG009 | Unclear clickable elements (no hover effect or underline) | 1. Hover over each item in both lists 2. No indication if text is clickable (e.g., link vs. plain text) |  | Medium | High | Open
BUG011 | List alignment and spacing inconsistency | 1. Compare spacing between bullets and text in both columns 2. Notice inconsistent vertical spacing |  | Low | Low | Open
BUG012 | Capitalization inconsistency in headings and items | 1. Review capitalization in "Panampally nagar wedding service", "Stage Decoration", etc. |  | Low | Low | Open
BUG013 | Archive sidebar shows future and inconsistent dates (e.g. February 2025) | 1. Navigate to the Privacy Policy page 2. Look at the archive sidebar 3. Note the presence of dates in the future (e.g. 2025) and irregular gaps in months/years |  | Low | Medium | Open
BUG014 | Random placeholder/gibberish text displayed on page | 1. Navigate to the Privacy Policy page 2. Scroll to the lower section 3. Observe random text like "rrrrrr...iuuuu..." |  | Low | Low | Open
BUG015 | “Learn more” on Decor for Wedding reloads the same page from the top instead of redirecting to a detail page or section | 1. Go to “Decor for Wedding” section 2. Click “Learn more” |  | Medium | Medium | Open
BUG016 | “Learn more” on Book Wedding Planner behaves like a refresh rather than redirecting | 1. Go to “Book Wedding Planner” section 2. Click “Learn more” |  | Medium | Medium | Open
BUG017 | “Learn more” on Destination Wedding does not work at all—no redirect, no refresh, no interaction | 1. Scroll to “Destination Wedding” section 2. Click “Learn more” button |  | High | High | Open
BUG018 | Multiple “Read more”/CTA elements appear interactive (hover color changes) but are non-clickable | 1. Navigate to various cards or content areas like “Wedding Cars,” “Culture Weddings,” etc. 2. Hover over any "Read more" or text sections meant for navigation/interaction. 3. Observe the color change on hover (suggesting interactivity). 4. Click the element — no redirect or action occurs. |  | High | High | Open
BUG019 | Several "Useful Links" are visually split across lines, making them unreadable or confusing (e.g., “Planner” appears multiple times). | 1. Scroll to the footer section. 2. Observe the formatting under "Useful Links". |  | Medium | Medium | Open
BUG020 | Social media icons (Facebook, Twitter, Instagram) are present but not linked to any URLs — they are non-functional. | 1. Scroll to footer. 2. Click any social media icon. 3. No navigation or action occurs. |  | High | High | Open
BUG021 | “Contact us .” has incorrect punctuation — extra space before the period, looks unprofessional. | 1. Scroll to "Contact us" section in footer. 2. Note the formatting issue. |  | Low | Low | Open
BUG022 | “Regd No:” is present but the value is missing, suggesting incomplete company info. | 1. Check "Contact us" section. 2. Locate the line with "Regd No:". 3. Observe it's blank. |  | Medium | High | Open
BUG023 | Broken visual alignment — address and contact info on the right overlaps in small screens or feels congested on medium screens. | 1. Resize the window to medium/small screens. 2. Observe the layout under "Contact us". |  | Medium | Medium | Open
DECOR
Bug ID | Bug Description | Steps to Reproduce | Screenshot | Severity | Priority | Status
BUG024 | Dropdown under “DECOR” menu shows only a vague “Types” item, which is unclear and non-informative to the user | 1. Hover over the DECOR menu in the top navigation bar. 2. Observe the dropdown content. 3. Only one item (“Types”) appears without any sub-options or clarity. |  | Medium | Medium | Open
BUG025 | Only the Home button functions; other navigation links like Contact Us do not load their respective pages | 1. Go to the website Decor. 2. Click on Contact Us or any link other than Home. 3. Observe that no navigation or page change occurs — only Home reloads or remains active. |  | High | High | Open
BUG026 | Google Plus icon redirects to unrelated Google Workspace Updates blog instead of a valid Google Plus page | 1. Scroll to the social media icon section in the footer. 2. Click on the Google Plus (G+) icon. 3. Observe the redirection to the Google Workspace blog instead of a valid Google Plus page. |  | Low | Medium | Open
BUG027 | Social media icons in the footer are non-functional; clicking on any icon (Twitter, Facebook, etc.) does not trigger any navigation or redirection | 1. Go to the bottom of the webpage. 2. Click on any of the social media icons (Twitter, Facebook, Google Plus, Instagram, YouTube, LinkedIn, RSS). 3. Observe that none of them redirect to the respective platforms. |  | Medium | High | Open
DESTINATION
Bug ID | Bug Description | Steps to Reproduce | Screenshot | Severity | Priority | Status
BUG028 | “The Planner” submenu item under DESTINATION does not redirect or perform any action when clicked | 1. Hover over the DESTINATION menu item in the main navigation. 2. Click on The Planner under the dropdown list. 3. No navigation or redirection takes place. |  | High | High | Open
CONTACT US
Bug ID | Bug Description | Steps to Reproduce | Screenshot | Severity | Priority | Status
BUG029 | "CALL +91 8943 906399" button in the Contact section does not redirect or initiate a call when clicked | 1.. Open the website www.weddingplannerskerala.com 2. Scroll to the Contact section of the website. |  | High | High | Open
BUG030 | Email addresses in the Contact section break into two lines, making them unreadable or hard to copy | 1. Open the website www.weddingplannerskerala.com 2.Scroll to the Contact section. |  | High | High | Open

## DEFECT DISTRIBUTION
DEFECT DISTRIBUTION GRAPH
MODULE NAME | DEFECT DISTRIBUTION
HOME PAGE | 23
DECOR | 4
DESTINATION | 1
CONTACT US | 2